## Automatic Gantt Chart
Tasks | Assigned To | Progress | Start | Due | Start on Day* | Duration* | User | Estimated Hours | Actual Hours | Estimated Cost | Actual Cost | Priority | Risk
- Brainstorming -
Brainstorm Session |  | 0% | 2021-04-02 | 2021-04-03 | 0 | 1 |  | 25 | 28 |  |  | 5 | 4
Concept Scetches |  | 0% | 2021-04-02 | 2021-04-03 | 0 | 1 | Alexandra Cuartin | 15 | 20 |  |  | 5 | 4
Submission for Approval (Brainstorm) |  | 0% | 2021-04-04 | 2021-04-04 | 2 | 1 | Victor Pascow | 10 | 8 |  |  | 5
- Design - | [7 empty] | 95 | 84 | 1600 | 1550 | 4 | 2
Fusion Part Design |  | 0% | 2021-04-05 | 2021-04-08 | 3 | 3 | Victor Pascow | 2 | 2 |  |  | 4 | 2
Fusion Assembly |  | 0% | 2021-04-08 | 2021-04-09 | 9 | 1 | Wendy Torrance | 48 | 40 | 500 | 450 | 3 | 2
Fusion Drawing Generation |  | 0% | 2021-04-10 | 2021-04-11 | 10 | 1 | Alexandra Cuartin | 45 | 42 | 300 | 325 | 2 | 1
Submission for Approval (Design) |  | 0% | 2021-04-12 | 2021-04-12 | 11 | 0 | Wendy Torrance |  |  | 800 | 775 | 5 | 2
- Prototyping - | [7 empty] | 112 | 98 | 350 | 250 | 4 | 3
Physical Assembly |  | 0% | 2021-04-13 | 2021-04-20 | 11 | 7 | Alexandra Cuartin | 72 | 72 | 350 | 250 | 5 | 5
Testing Procedure Development |  | 0% | 2021-04-20 | 2021-04-23 | 18 | 3 | Laurie Strode | 36 | 24 |  |  | 3 | 3
Product Testing and Data Collection |  | 0% | 2021-04-24 | 2021-04-25 | 22 | 1 | Alexandra Cuartin | 4 | 2 |  |  | 5 | 1
Reiteration / Resign |  | 0% | 2021-04-25 | 2021-04-25 | 23 | 0 |  | 28 | 28 |  |  | 4
- Documentation - | [6 empty] | Andy Barclay | 5 | 4 |  |  | 5
Powerpoint Presentation for Results |  | 0% | 2021-04-25 | 2021-04-27 | 23 | 2 | Wendy Torrance | 10 | 10 |  |  | 5
Design Process Paper Write Up |  | 0% | 2021-04-27 | 2021-04-27 | 25 | 0 | Alexandra Cuartin | 10 | 12 |  |  | 5
- Demonstration - | [6 empty] | Alexandra Cuartin | 1 | 0.5 |  |  | 2
Demonstration Scheduled |  | 0% | 2021-04-27 | 2021-04-27 | 25 | 0 | Jason Myers | 1 | 1 |  |  | 5
Final Test Day |  | 0% | 2021-04-27 | 2021-04-27 | 25 | 0 | Alexandra Cuartin | 1 | 0.5 |  |  | 3
- Total Project Duration - | [5 empty] | 21 |  | 53 | 50 | 855 | 655 | 4 | 3
[7 empty] | Laurie Strode | 10 | 9 | 200 | 150 | 5 | 3
[7 empty] | Alexandra Cuartin | 15 | 10 | 450 | 300 | 4 | 1
[7 empty] | Wendy Torrance | 20 | 24 | 100 | 100 | 3
[7 empty] | Victor Pascow | 1 | 1
[7 empty] | Alexandra Cuartin | 5 | 4 | 105 | 105 | 5 | 4
[7 empty] | Victor Pascow | 1 | 1
[7 empty] | Victor Pascow | 1 | 1
[8 empty] | 9.5 | 9.5 | 100 | 150 | 4 | 3
[7 empty] | Jason Myers | 3 | 3 | 100 | 150 | 4 | 3
[7 empty] | Jason Myers | 1 | 1
[7 empty] | Alexandra Cuartin | 1 | 1 |  |  | 4 | 4
[7 empty] | Alex Spine | 0.5 | 0.5 |  |  | 4 | 1
[7 empty] | Alexandra Cuartin | 4 | 3 | 150 | 200 | 5 | 2
[7 empty] | Victor Pascow | 15 |  | 250 | 250 | 5 | 1
[7 empty] | Wendy Torrance | 2
[7 empty] | Andy Barclay | 1 |  |  |  | 5 | 1
*Cells calculated automatically